## Overall processing
Chunk Name | Initial Processing Time (minutes) | Initial report verification (minutes) | GCP marking (minutes) | Final Processing Time (minutes) | Final Verification (minutes) | Total task (minutes) | Total task (hours) | Start | Stop | Start date | End date
Chunk 1 | 122 | 2 | 5 | 374 | 3 | 506 | 8.4333 | 43370.0139 | 43370.3653 | 2018-09-27 00:20 | 2018-09-27 08:46
Chunk 2 | 154 | 2 | 5 | 433 | 3 | 597 | 9.95 | 43370.3653 | 43370.7799 | 2018-09-27 08:46 | 2018-09-27 18:43
Chunk 3 | 167 | 2 | 5 | 381 | 3 | 558 | 9.3 | 43370.7799 | 43371.1674 | 2018-09-27 18:43 | 2018-09-28 04:01
Chunk 4 | 200 | 3 | 10 | 492 | 4 | 709 | 11.8167 | 43371.1674 | 43371.6597 | 2018-09-28 04:01 | 2018-09-28 15:50
Chunk 5 | 86 | 2 | 5 | 259 | 3 | 355 | 5.9167 | 43371.6597 | 43371.9062 | 2018-09-28 15:50 | 2018-09-28 21:45
Chunk 6 | 102 | 2 | 5 | 324 | 3 | 436 | 7.2667 | 43371.9062 | 43372.209 | 2018-09-28 21:45 | 2018-09-29 05:01
Chunk 7 | 139 | 2 | 5 | 362 | 3 | 511 | 8.5167 | 43372.209 | 43372.5639 | 2018-09-29 05:01 | 2018-09-29 13:32
Chunk 8 | 155 | 2 | 5 | 388 | 3 | 553 | 9.2167 | 43372.5639 | 43372.9479 | 2018-09-29 13:32 | 2018-09-29 22:45
Chunk 9 | 212 | 3 | 10 | 454 | 4 | 683 | 11.3833 | 43372.9479 | 43373.4222 | 2018-09-29 22:45 | 2018-09-30 10:08
Chunk 10 | 122 | 2 | 5 | 376 | 3 | 508 | 8.4667 | 43373.4222 | 43373.775 | 2018-09-30 10:08 | 2018-09-30 18:36
Chunk 11 | 207 | 3 | 10 | 495 | 4 | 719 | 11.9833 | 43373.775 | 43374.2743 | 2018-09-30 18:36 | 2018-10-01 06:35
Chunk 12 | 186 | 2 | 5 | 442 | 3 | 638 | 10.6333 | 43374.2743 | 43374.7174 | 2018-10-01 06:35 | 2018-10-01 17:13
Chunk 13 | 165 | 2 | 5 | 415 | 3 | 590 | 9.8333 | 43374.7174 | 43375.1271 | 2018-10-01 17:13 | 2018-10-02 03:03
Chunk 14 | 142 | 2 | 5 | 420 | 3 | 572 | 9.5333 | 43375.1271 | 43375.5243 | 2018-10-02 03:03 | 2018-10-02 12:35
Chunk 15 | 128 | 2 | 5 | 341 | 3 | 479 | 7.9833 | 43375.5243 | 43375.8569 | 2018-10-02 12:35 | 2018-10-02 20:34
Chunk 16 | 231 | 3 | 10 | 520 | 4 | 768 | 12.8 | 43375.8569 | 43376.3903 | 2018-10-02 20:34 | 2018-10-03 09:22
Chunk 17 | 59 | 2 | 5 | 187 | 3 | 256 | 4.2667 | 43376.3903 | 43376.5681 | 2018-10-03 09:22 | 2018-10-03 13:38
Chunk 18 | 39 | 2 | 5 | 145 | 3 | 194 | 3.2333 | 43376.5681 | 43376.7028 | 2018-10-03 13:38 | 2018-10-03 16:52
Chunk 19 | 69 | 2 | 5 | 245 | 3 | 324 | 5.4 | 43376.7028 | 43376.9278 | 2018-10-03 16:52 | 2018-10-03 22:16
Chunk 20 | 94 | 2 | 5 | 300 | 3 | 404 | 6.7333 | 43376.9278 | 43377.2083 | 2018-10-03 22:16 | 2018-10-04 05:00
| 2779 | 44 | 120 | 7353 | 64 | 10360 | 172.6667

## Task wise processing
Chunk Name | Initial Processing Time (minutes) | Initial report verification (minutes) | GCP marking (minutes) | Final Processing Time (minutes) | Final Verification (minutes) | Initial processing start time | initial processing stop time | Initial report verification start time | Initial report verification stop time | GCP marking start time | GCP marking stop time | Final processing start time | Final processing stop time | Final verification start time | Final Verification stop time | Computer resource allocated | Human resource allocated
Chunk 1 | 122 | 2 | 5 | 374 | 3
Chunk 2 | 154 | 2 | 5 | 433 | 3
Chunk 3 | 167 | 2 | 5 | 381 | 3
Chunk 4 | 200 | 3 | 10 | 492 | 4
Chunk 5 | 86 | 2 | 5 | 259 | 3
Chunk 6 | 102 | 2 | 5 | 324 | 3
Chunk 7 | 139 | 2 | 5 | 362 | 3
Chunk 8 | 155 | 2 | 5 | 388 | 3
Chunk 9 | 212 | 3 | 10 | 454 | 4
Chunk 10 | 122 | 2 | 5 | 376 | 3
Chunk 11 | 207 | 3 | 10 | 495 | 4
Chunk 12 | 186 | 2 | 5 | 442 | 3
Chunk 13 | 165 | 2 | 5 | 415 | 3
Chunk 14 | 142 | 2 | 5 | 420 | 3
Chunk 15 | 128 | 2 | 5 | 341 | 3
Chunk 16 | 231 | 3 | 10 | 520 | 4
Chunk 17 | 59 | 2 | 5 | 187 | 3
Chunk 18 | 39 | 2 | 5 | 145 | 3
Chunk 19 | 69 | 2 | 5 | 245 | 3
Chunk 20 | 94 | 2 | 5 | 300 | 3